## back of envelope
Back of the Envelope Analysis
International Plaza Four
INCOME CALCULATIONS |  |  |  | per RSF | Annual
Gross Building Area |  |  |  |  | 260000
Rentable Area Ratio per FAR |  |  |  |  | 95%
Rentable Area |  |  |  |  | 247000
Rental Income per Rentable Square Foot |  |  |  | 31 | 7657000
Parking Income |  |  |  | 0 | 0
Gross Income |  |  |  | 31 | 7657000
times: Occupancy Rate |  |  |  | 95%
Effective Gross Income |  |  |  |  | 7274150
less: Operating Expenses |  |  |  | 11 | 2717000
Net Operating Income |  |  |  | 18.45 | 4557150
DEVELOPMENT COST CALCULATIONS |  |  |  |  | Total
per RSF
HARD COST
Earthwork |  |  | 0.04 |  | 9880
Storm Sewer |  |  | 0 |  | 0
Building Construction |  |  | 100.33 |  | 24781510
Other Construction |  |  | 1.62 |  | 400140
Parking Deck |  |  | 42.14 |  | 10408580
Contingency - Hard |  |  | 2.69 |  | 664430
Subtotal Hard Cost |  |  |  |  | 36264540
SOFT COST
Real Esate Taxes |  |  | 0.2 |  | 49400
Special Fees |  |  | 4.29 |  | 1059630
Project Administration |  |  | 0.24 |  | 59280
Architect/Engineering |  |  | 2.09 |  | 516230
Insurance |  |  | 2.75 |  | 679250
Testing/Inspection/Permits |  |  | 0.58 |  | 143260
Landscape/Irrigation |  |  | 1.61 |  | 397670
Signage/Monumentation |  |  | 0.17 |  | 41990
Special Features Share Cost |  |  | 0.2 |  | 49400
Tenant Improvements |  |  | 22 |  | 5434000
Leasing Commissions |  |  | 7.81 |  | 1929070
Closing/Title Fees |  |  | 0.12 |  | 29640
Legal |  |  | 0.32 |  | 79040
Financing |  |  | 0.99 |  | 244530
Interim interest |  |  | 3.63 |  | 896610
Advertising/Promotion |  |  | 0.22 |  | 54340
Leasing/Salary Expenses |  |  | 0.61 |  | 150670
Tenant Inducements |  |  | 3 |  | 741000
Contingency - Soft |  |  | 0.2 |  | 49400
Subtotal Soft Cost (before Overhead) |  |  |  |  | 12555010
Corporate Overhead @ |  | 3.5% |  | 48819550 | 1708684.25
Subtotal Soft Cost |  |  |  |  | 14263694.25
SUBTOTAL HARD & SOFT COSTS |  |  |  |  | 50528234.25
LAND COST
Expected Land Cost |  |  | 22 |  | 5434000
Infrastructure |  |  | 0
| Total Land Cost |  | 22 | 22 | 5434000
TOTAL DEVELOPMENT COSTS |  |  |  |  | 55962234.25
NET CAP RATE CALCULATIONS
Net Operating Income |  |  |  |  | 18.45
divided by: Total Development Costs |  |  |  |  | #REF!
Return On Total Costs |  |  |  |  | #REF!
less: Required Spread |  |  |  |  | 1.25%
Required Disposition Cap Rate |  |  |  |  | #REF!
less: Market Cap Rate |  |  |  |  | 6.75%
Net Cap Rate |  |  |  |  | #REF!
Indicated Decision |  |  |  |  | #REF!
JUSTIFIED LAND PRICE CALCULATIONS
Market Cap Rate |  |  |  |  | 6.75%
plus: Required Spread |  |  |  |  | 1.25%
Required Return on Costs |  |  |  |  | 8%
times: ODC |  |  |  |  | 48819550
Income To ODC |  |  |  |  | 3905564
Net Operating Income |  |  |  |  | 18.45
less: Income to ODC |  |  |  |  | 3905564
Income To Land |  |  |  |  | -3905545.55
divided by: Required Return on Costs |  |  |  |  | 8%
Justified Land Price |  |  |  |  | -48819319.375
BREAK-EVEN GROSS RENT CALCULATIONS
Total Development Costs |  |  |  |  | #REF!
times: Required Return on Costs |  |  |  |  | 8%
Required NOI |  |  |  |  | #REF!
plus: Operating Expenses |  |  |  |  | 11
Required Effective Gross |  |  |  |  | #REF!
divided by:Pro Forma Occupancy Rate |  |  |  |  | 95%
Break-Even Gross Rent |  |  |  |  | #REF!

## Construction Draw
Input Box
construction period | 24
total cost | 36254660
time start
time end
period cost spent | 0
Time Table
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Monthly Cost | 108030.303 | 117099.0021 | 218064.7947 | 381604.1989 | 627532.8132 | 969741.2556 | 1408224.2558 | 1921695.6651 | 2464305.3186 | 2969625.9566 | 3362842.1588 | 3578564.2775
Cummulative Cost | 108030.303 | 225129.3051 | 443194.0998 | 824798.2987 | 1452331.112 | 2422072.3676 | 3830296.6234 | 5751992.2885 | 8216297.6071 | 11185923.5637 | 14548765.7225 | 18127330
Month | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24
Monthly Cost | 3578564.2775 | 3362842.1588 | 2969625.9566 | 2464305.3186 | 1921695.6651 | 1408224.2558 | 969741.2556 | 627532.8132 | 381604.1989 | 218064.7947 | 117099.0021 | 108030.303
Cummulative Cost | 21705894.2775 | 25068736.4363 | 28038362.3929 | 30502667.7115 | 32424363.3766 | 33832587.6324 | 34802328.888 | 35429861.7013 | 35811465.9002 | 36029530.6949 | 36146629.697 | 36254660
Cumulative Cost
cumulative cost | construction period
48940.0942 | 0
297198.8778 | 2.4
1302641.5031 | 4.8
4171811.7702 | 7.2
9942953.538 | 9.6
18127330 | 12
26311706.462 | 14.4
32082848.2298 | 16.8
34952018.4969 | 19.2
35957461.1222 | 21.6
36205719.9058 | 24

## development_budget
DEVELOPMENT COST CALCULATIONS |  |  |  | Total |  |  | MONTHLY PAYMENTS
|  | per RSF |  |  |  |  | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 |  | Unspent Reserves
HARD COST
Earthwork |  | 0.04 |  | 9880 |  | at closing | MONTHLY PAYMENTS 0: 9880 | 9880 | 0
Storm Sewer |  | 0 |  | 0 |  | S-curve | [25 empty] | 0 | 0
Building Construction |  | 100.33 |  | 24781510 |  | S-curve | [25 empty] | 0
Other Construction |  | 1.62 |  | 400140 |  | S-curve | [25 empty] | 0
Parking Deck |  | 42.14 |  | 10408580 |  | S-curve | [25 empty] | 0
Contingency - Hard |  | 2.69 |  | 664430 |  | S-curve | [25 empty] | 0
Hard Cost Monthly Draws / Sum of S-curve |  |  |  | 36254660 |  |  |  | 108030.303 | 117099.0021 | 218064.7947 | 381604.1989 | 627532.8132 | 969741.2556 | 1408224.2558 | 1921695.6651 | 2464305.3186 | 2969625.9566 | 3362842.1588 | 3578564.2775 | 3578564.2775 | 3362842.1588 | 2969625.9566 | 2464305.3186 | 1921695.6651 | 1408224.2558 | 969741.2556 | 627532.8132 | 381604.1989 | 218064.7947 | 117099.0021 | 108030.303 | 36254660 | 0
Subtotal Hard Cost |  | 0 |  | 36264540
SOFT COST
Real Esate Taxes |  | 0.2 |  | 49400 |  | annual | MONTHLY PAYMENTS 12: 24700; MONTHLY PAYMENTS 24: 24700 | 49400 | 0
Special Fees |  | 4.29 |  | 1059630 |  | quarterly | MONTHLY PAYMENTS 3: 132453.75; MONTHLY PAYMENTS 6: 132453.75; MONTHLY PAYMENTS 9: 132453.75; MONTHLY PAYMENTS 12: 132453.75; MONTHLY PAYMENTS 15: 132453.75; MONTHLY PAYMENTS 18: 132453.75; MONTHLY PAYMENTS 21: 132453.75; MONTHLY PAYMENTS 24: 132453.75 | 1059630 | 0
Project Administration |  | 0.24 |  | 59280 |  | monthly |  | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 2470 | 59280 | 0
Architect/Engineering |  | 2.09 |  | 516230 |  | 75% at closing, 25% monthly | 387172.5 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 5377.3958 | 516230 | 0
Insurance |  | 2.75 |  | 679250 |  | quarterly | MONTHLY PAYMENTS 3: 84906.25; MONTHLY PAYMENTS 6: 84906.25; MONTHLY PAYMENTS 9: 84906.25; MONTHLY PAYMENTS 12: 84906.25; MONTHLY PAYMENTS 15: 84906.25; MONTHLY PAYMENTS 18: 84906.25; MONTHLY PAYMENTS 21: 84906.25; MONTHLY PAYMENTS 24: 84906.25 | 679250 | 0
Testing/Inspection/Permits |  | 0.58 |  | 143260 |  | quarterly | MONTHLY PAYMENTS 3: 17907.5; MONTHLY PAYMENTS 6: 17907.5; MONTHLY PAYMENTS 9: 17907.5; MONTHLY PAYMENTS 12: 17907.5; MONTHLY PAYMENTS 15: 17907.5; MONTHLY PAYMENTS 18: 17907.5; MONTHLY PAYMENTS 21: 17907.5; MONTHLY PAYMENTS 24: 17907.5 | 143260 | 0
Landscape/Irrigation |  | 1.61 |  | 397670 |  | last 6 months | MONTHLY PAYMENTS 19: 66278.3333; MONTHLY PAYMENTS 20: 66278.3333; MONTHLY PAYMENTS 21: 66278.3333; MONTHLY PAYMENTS 22: 66278.3333; MONTHLY PAYMENTS 23: 66278.3333; MONTHLY PAYMENTS 24: 66278.3333 | 397670 | 0
Signage/Monumentation |  | 0.17 |  | 41990 |  | last 6 months | MONTHLY PAYMENTS 19: 6998.3333; MONTHLY PAYMENTS 20: 6998.3333; MONTHLY PAYMENTS 21: 6998.3333; MONTHLY PAYMENTS 22: 6998.3333; MONTHLY PAYMENTS 23: 6998.3333; MONTHLY PAYMENTS 24: 6998.3333 | 41990 | 0
Special Features Share Cost |  | 0.2 |  | 49400 |  | last 6 months | MONTHLY PAYMENTS 19: 8233.3333; MONTHLY PAYMENTS 20: 8233.3333; MONTHLY PAYMENTS 21: 8233.3333; MONTHLY PAYMENTS 22: 8233.3333; MONTHLY PAYMENTS 23: 8233.3333; MONTHLY PAYMENTS 24: 8233.3333 | 49400 | 0
Tenant Improvements |  | 22 |  | 5434000 | 40% | lease-up schedule | MONTHLY PAYMENTS 19: 362266.6667; MONTHLY PAYMENTS 20: 362266.6667; MONTHLY PAYMENTS 21: 362266.6667; MONTHLY PAYMENTS 22: 362266.6667; MONTHLY PAYMENTS 23: 362266.6667; MONTHLY PAYMENTS 24: 362266.6667 | 2173600 | 3260400
Leasing Commissions |  | 7.81 |  | 1929070 | 40% | lease-up schedule | MONTHLY PAYMENTS 19: 128604.6667; MONTHLY PAYMENTS 20: 128604.6667; MONTHLY PAYMENTS 21: 128604.6667; MONTHLY PAYMENTS 22: 128604.6667; MONTHLY PAYMENTS 23: 128604.6667; MONTHLY PAYMENTS 24: 128604.6667 | 771628 | 1157442
Tenant Inducements |  | 3 |  | 741000 | 40% | lease-up schedule | MONTHLY PAYMENTS 19: 49400; MONTHLY PAYMENTS 20: 49400; MONTHLY PAYMENTS 21: 49400; MONTHLY PAYMENTS 22: 49400; MONTHLY PAYMENTS 23: 49400; MONTHLY PAYMENTS 24: 49400 | 296400 | 444600
Closing/Title Fees |  | 0.12 |  | 29640 |  | at closing | MONTHLY PAYMENTS 0: 29640 | 29640 | 0
Legal |  | 0.32 |  | 79040 |  | monthly |  | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 3293.3333 | 79040 | 0
Financing |  | 0.99 |  | 244530 |  | at closing | MONTHLY PAYMENTS 0: 244530 | 244530 | 0
Interim interest |  |  |  | 1509031.2527 |  | monthly |  | 34.9917 | 417.7229 | 833.928 | 1609.1943 | 2966.4084 | 5199.4265 | 8652.3414 | 13670.446 | 20524.8676 | 29325.3079 | 39946.5936 | 51998.1371 | 64856.379 | 77760.1605 | 89945.627 | 100781.6097 | 109866.2926 | 117061.4079 | 122463.4613 | 126331.6863 | 129001.6231 | 130810.0187 | 132045.617 | 132928.0042 | 1509031.2527 | 0
Advertising/Promotion |  | 0.22 |  | 54340 |  | quarterly | MONTHLY PAYMENTS 3: 6792.5; MONTHLY PAYMENTS 6: 6792.5; MONTHLY PAYMENTS 9: 6792.5; MONTHLY PAYMENTS 12: 6792.5; MONTHLY PAYMENTS 15: 6792.5; MONTHLY PAYMENTS 18: 6792.5; MONTHLY PAYMENTS 21: 6792.5; MONTHLY PAYMENTS 24: 6792.5 | 54340 | 0
Leasing/Salary Expenses |  | 0.61 |  | 150670 |  | monthly |  | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 6277.9167 | 150670 | 0
Contingency - Soft |  | 0.2 |  | 49400 |  | annual | MONTHLY PAYMENTS 12: 24700; MONTHLY PAYMENTS 24: 24700 | 49400 | 0
Subtotal Soft Cost (before Overhead) |  |  |  | 13216831.2527
Corporate Overhead @ | 3.5% |  | 49481371.2527 | 1731847.9938 |  | at substantial completion | MONTHLY PAYMENTS 24: 1731847.9938 | 1731847.9938 | 0
Subtotal Soft Cost |  |  |  | 14948679.2465
SUBTOTAL HARD & SOFT COSTS |  |  |  | 51213219.2465
LAND COST
Expected Land Cost |  | 22 |  | 5434000 |  | at closing | MONTHLY PAYMENTS 0: 5434000
Infrastructure |  | 0 |  | 0 |  | first 6 months
TOTAL DEVELOPMENT COSTS |  |  |  | 56647219.2465 |  |  | 6105222.5 | 125483.9405 | 134935.3709 | 478377.3685 | 400632.0391 | 647917.8675 | 1234419.3279 | 1434295.243 | 1952784.757 | 2744308.8321 | 3016369.9103 | 3420207.3982 | 3939441.0604 | 3660839.3023 | 3458020.9651 | 3319050.2295 | 2582505.5742 | 2048980.6036 | 1784764.3095 | 1731404.696 | 1393064.4787 | 1391865.8012 | 988074.7925 | 888344.5983 | 2903466.2802
less Construction Loan | [6 empty] | 9880 | 108065.2946 | 117516.7251 | 218898.7227 | 383213.3932 | 630499.2216 | 974940.682 | 1416876.5972 | 1935366.1111 | 2484830.1863 | 2998951.2645 | 3402788.7524 | 3630562.4146 | 3643420.6565 | 3440602.3193 | 3059571.5837 | 2565086.9284 | 2031561.9577 | 1525285.6637 | 1092204.7168 | 753864.4996 | 510605.822 | 348874.8134 | 249144.6191 | 240958.3071
Required Equity Contribution | [6 empty] | 6095342.5 | 17418.6458 | 17418.6458 | 259478.6458 | 17418.6458 | 17418.6458 | 259478.6458 | 17418.6458 | 17418.6458 | 259478.6458 | 17418.6458 | 17418.6458 | 308878.6458 | 17418.6458 | 17418.6458 | 259478.6458 | 17418.6458 | 17418.6458 | 259478.6458 | 639199.9792 | 639199.9792 | 881259.9792 | 639199.9792 | 639199.9792 | 2662507.973 | 14011205.9938
|  |  |  | Beginning Balance |  |  | 9880 | 9880 | 117945.2946 | 235462.0197 | 454360.7424 | 837574.1356 | 1468073.3572 | 2443014.0393 | 3859890.6365 | 5795256.7476 | 8280086.9339 | 11279038.1984 | 14681826.9508 | 18312389.3654 | 21955810.0219 | 25396412.3412 | 28455983.9248 | 31021070.8532 | 33052632.8109 | 34577918.4746 | 35670123.1914 | 36423987.691 | 36934593.513 | 37283468.3264 | 37532612.9455
|  |  |  | Accrued Interest | 4.25% |  | 0 | 34.9917 | 417.7229 | 833.928 | 1609.1943 | 2966.4084 | 5199.4265 | 8652.3414 | 13670.446 | 20524.8676 | 29325.3079 | 39946.5936 | 51998.1371 | 64856.379 | 77760.1605 | 89945.627 | 100781.6097 | 109866.2926 | 117061.4079 | 122463.4613 | 126331.6863 | 129001.6231 | 130810.0187 | 132045.617 | 132928.0042 | 1509031.2527
|  |  |  | Construction Draw |  |  |  | 108030.303 | 117099.0021 | 218064.7947 | 381604.1989 | 627532.8132 | 969741.2556 | 1408224.2558 | 1921695.6651 | 2464305.3186 | 2969625.9566 | 3362842.1588 | 3578564.2775 | 3578564.2775 | 3362842.1588 | 2969625.9566 | 2464305.3186 | 1921695.6651 | 1408224.2558 | 969741.2556 | 627532.8132 | 381604.1989 | 218064.7947 | 117099.0021 | 108030.303
|  |  |  | Ending Balance |  |  | 9880 | 117945.2946 | 235462.0197 | 454360.7424 | 837574.1356 | 1468073.3572 | 2443014.0393 | 3859890.6365 | 5795256.7476 | 8280086.9339 | 11279038.1984 | 14681826.9508 | 18312389.3654 | 21955810.0219 | 25396412.3412 | 28455983.9248 | 31021070.8532 | 33052632.8109 | 34577918.4746 | 35670123.1914 | 36423987.691 | 36934593.513 | 37283468.3264 | 37532612.9455 | 37773571.2527
SOURCES OF FUNDS
Construction Loan |  |  |  | 37773571.2527
Equity Contributions |  |  |  | 14011205.9938
Equity Reserves |  |  |  | 4862442
Total Sources |  |  |  | 56647219.2465
Unspent Development Funds |  |  |  | 4862442