## Master Budget
One Anikeeff Place Budget
Category | 1/5/12 Budget |  | DMA Budget (2/2/12) |  | Comments | SD Pricing Budget (7/27/12) |  | 50% DD Budget (8/21/12) |  | Comments
| 250000 |  | 250000 |  |  | 263810 |  | 270294
| Cost | per RSF | Cost | per RSF |  | Cost | per RSF | Cost | per RSF
LAND COSTS
Land Acquisition | 5000000 | 20 | 5179000 | 20.716 | from original Proforma | 2920155.5 | 11.0692 | 2920155.5 | 10.8036 | from original Proforma
Closing Expenses
INFRASHARE | [5 empty] | 2258844.5 | 8.5624 | 2258844.5 | 8.357 | $13,553,067 Infra Budget divided by 6
TOTAL LAND COSTS | 5000000 | 20 | 5179000 | 20.716 |  | 5179000 | 19.6316 | 5179000 | 19.1606
CONSTRUCTION HARD COSTS
General Contractor/Construction Manager Contract | 21500000 | 86 | 21500000 | 86 | Conceptual Estimate | 27356749 | 103.6987 | 38760311 | 143.4006
Landscaping | 300000 | 1.2 | 300000 | 1.2 | Conceptual Estimate | 0 | 0 | 0 | 0
Sitework & Grading | 0 | 0 |  |  |  | 2181071 | 8.2676 | 0 | 0
Parking | 6800000 | 27.2 | 9500000 | 38 | Conceptual Estimate | 9879385 | 37.4489 | 0 | 0 | 48,500/space incl in GC
Other Direct Hard Costs
Interior/Exterior Signage | 100000 | 0.4 | 100000 | 0.4 | SPE Estimate | 100000 | 0.37906 | 100000 | 0.36997 | SPE Estimate
Furniture, Fixtures & Equipment | 50000 | 0.2 | 50000 | 0.2 | SPE Estimate - Lease Fitness Equipment | 50000 | 0.18953 | 50000 | 0.18498 | SPE Estimate - Lease Fitness Equipment
Owner-Furnished Construction Items
Underground Electrical Work - (MTEMC) | [9 empty] | Included in Sitework & Grading
Other (detail as appropriate)
Other (detail as appropriate)
Owner Hard Cost Contingency (see note) | 0 | 0 | 0 | 0 |  | 1182516.15 | 4.4825 | 1000000 | 3.6997 | 1.5% Contingency on Hard Costs
TOTAL CONSTRUCTION HARD COSTS | 28750000 | 115 | 31450000 | 125.8 |  | 40749721.15 | 154.4662 | 39910311 | 147.6552
PROJECT SOFT COSTS
Architectural/Engineering Design
Architectural | 1000000 | 4 | 825000 | 3.3 | Duda Paine Estimate | 962500 | 3.6485 | 1390750 | 5.1453 | DudaPaine Proposal + 10%
Environmental
Site/Civil Engineering |  |  | 87500 | 0.35 | Duda Paine Estimate | 79750 | 0.3023 | 79750 | 0.29505 | Ragan Smith Proposal + 10%
Geotechnical |  |  | 50000 | 0.2 | Duda Paine Estimate | 50000 | 0.18953 | 50000 | 0.18498 | Soil Testing - SPE Estimate
Structural Engineering |  |  | 141300 | 0.5652 | Duda Paine Estimate | 115500 | 0.43782 | 115500 | 0.42731 | DudaPaine Proposal + 10%
Structural Engineering - Structured Parking | [5 empty] | 152460 | 0.57792 | 152460 | 0.56405 | DudaPaine Proposal + 10%
MEP/Fire Protection - Full Service |  |  | 60250 | 0.241 | Duda Paine Estimate | 132550 | 0.50244 | 132550 | 0.49039 | DudaPaine Proposal + 10%
Landscape Design |  |  | 60000 | 0.24 | Duda Paine Estimate | 66000 | 0.25018 | 66000 | 0.24418 | DudaPaine Proposal + 10%
Interior Design
Traffic Consultant | [5 empty] | 25000 | 0.094765 | 25000 | 0.092492 | SPE Estimate
Elevator Consultant | [5 empty] | 14740 | 0.055874 | 14740 | 0.054533 | Lerch Bates Proposal + 10%
Lighting Consultant | [5 empty] | 20000 | 0.075812 | 20000 | 0.073994 | SPE Estimate
Acoustical Consultant
Misc. Consultant | [5 empty] | 20000 | 0.075812 | 20000 | 0.073994
Signage & Graphics Design | [5 empty] | 15000 | 0.056859 | 15000 | 0.055495 | SPE Estimate
Curtainwall/Waterproofing Consultant | [5 empty] | 88000 | 0.33357 | 88000 | 0.32557 | W&A Proposal + 10%
Commissioning | [5 empty] | 63000 | 0.23881 | 63000 | 0.23308 | exp Proposal dated 6/25/12
Accessibility Consultant (ADA/FHA) | [5 empty] | 5000 | 0.018953 | 5000 | 0.018498 | SPE Estimate
Sustainability Consulting/Certification (eg, LEED) |  |  | 40000 | 0.16 | SPE Estimate | 42592 | 0.16145 | 42592 | 0.15758 | exp Proposal + USGBC Fees
ALTA Survey | 12500 | 0.05 | [5 empty] | 105592
Engineering Peer Review | [5 empty] | 30000 | 0.11372 | 30000 | 0.11099
Subtotal, Architectural/Engineering Design | 1012500 | 4.05 | 1264050 | 5.0562 |  | 1882092 | 7.1343 | 2415934 | 8.5475
Approvals & Oversight
Expeditor
Permits & Fees | 400000 | 1.6 | 400000 | 1.6 | SPE Estimate | 1650000 | 6.2545 | 1650000 | 6.1045 | per CoF Fee Schedules
Cost Estimating |  |  | 34500 | 0.138 |  | 0 |  | 0 |  | Using GC to estimate costs
Testing & Inspections | 250000 | 1 | 250000 | 1 | SPE Estimate | 132000 | 0.50036 | 132000 | 0.48836 | PSI Proposal + 10%
Owner Development Monitoring Consultant | [5 empty] | 110000 | 0.41697 | 110000 | 0.40696 | Pond Robinson Estimate + 10%
Owner Soft Cost Contingency (see note) | 0 |  | 0 |  |  | 56462.76 | 0.21403 | 72478.02 | 0.26815 | 3% Contingency of Soft Costs
Subtotal, Approvals & Oversight | 650000 | 2.6 | 684500 | 2.738 |  | 1948462.76 | 7.3859 | 1964478.02 | 7.2679
Project Administration & Overhead
Development Fee | 2290000 | 9.16 | 1037656.5 | 4.1506 | 3% of all Hard & Soft Costs | 1347908.2773 | 5.1094 | 1261382 | 4.6667 | 3% of all Hard & Soft Costs
Development Manager Reimbursable Expenses | 30000 | 0.12 | 460000 | 1.84 |  | 0 |  | 0
Subtotal, Project Administration & Overhead | 2320000 | 9.28 | 1497656.5 | 5.9906 |  | 1347908.2773 | 5.1094 | 1261382 | 4.6667
Financing
Construction Interest | 1147516 | 4.5901
Lender's Architect
Lender's Counsel
Appraisal Fees
Loan Settlement Costs | 189745 | 0.75898
Recording Costs - general | 20000 | 0.08 | 20000 | 0.08 |  | 0 | 0 | 0 | 0
Transfer Tax - Deed |  |  | 25000 | 0.1 |  | 0 |  | 0 |  | Moved to Real Estate Taxes below
Transfer Tax - Mortgage
State Recordation Stamps
Title Insurance | 45000 | 0.18 | 45000 | 0.18 |  | 0 | 0 | 0 | 0
Subtotal, Financing Costs | 1402261 | 5.609 | 90000 | 0.36 |  | 0 | 0 | 0 | 0
Marketing & Leasing
Advertising and Public Relations | 125000 | 0.5 | 125000 | 0.5 | SPE Estimate | 100000 | 0.37906 | 100000 | 0.36997 | SPE Estimate
Promotional Events
Marketing Flyers/Brochures
Models, Renderings, Displays
Marketing Office
Leasing Signage
Photography
Leasing Commissions | 2463825 | 9.8553 | 2463825 | 9.8553 | 6% on $26.00 w/ 2.5% esc - Average 6 years | 2401736.7924 | 9.104 | 2696001 | 9.9743 | 6% on $25.50 w/ 2.5% esc - Average 6 years
Leasing Expenses | 75000 | 0.3 | 75000 | 0.3 |  | 0 | 0 | 0 | 0
Tenant Improvements & Allowances | 7125000 | 28.5 | 7500000 | 30 | $30.00 per RSF | 6641416.75 | 25.175 | 7363440 | 27.2423 | $26.50 per RSF
Lease-Up Deficit | 425000 | 1.7 | 425000 | 1.7 |  | 0 | 0 | 0 | 0 | No interest payments
Subtotal, Marketing & Leasing Costs | 10213825 | 40.8553 | 10588825 | 42.3553 |  | 9143153.5424 | 34.6581 | 10159441 | 37.5866
Legal, Insurance & Accounting
Legal, Permitting & Entitlements | 150000 | 0.6 | 150000 | 0.6 | SPE Estimate | 150000 | 0.56859 | 150000 | 0.55495 | SPE Estimate
Legal, Leasing
Legal, Financing
Accounting and Auditing
Insurance - Builder's Risk | 25000 | 0.1
Insurance - Owner-Controlled Liability Program
Bonds/Letters of Credit
Subtotal, Legal, Insurance & Accounting Costs | 175000 | 0.7 | 150000 | 0.6 |  | 150000 | 0.56859 | 150000 | 0.55495
Operating Costs
Real Estate Taxes - Land |  |  | 0 |  |  | 25000 | 0.094765 | 25000 | 0.092492
Real Estate Taxes - Building
Misc. Operating Expenses
Subtotal, Operating Costs | 0 | 0 | 0 | 0 |  | 25000 | 0.094765 | 25000 | 0.092492
TOTAL PROJECT SOFT COSTS | 15773586 | 63.0943 | 14275031.5 | 57.1001 |  | 14496616.5797 | 54.951 | 15976235.02 | 58.7162
OWNER PROJECT CONTINGENCY | 1075000 | 4.3 | 825000 | 3.3 |  | 75000 | 0.2843 | 75000 | 0.27748 | Reduced due to Hard Cost Contingency
PROJECT TOTAL | 50598586 | 202.3943 | 51729031.5 | 206.9161 |  | 60500337.7297 | 229.333 | 61140546.02 | 225.8095